## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: NetSecure | [6 empty] | INSTUTUTE & DEPARTMENT NAME: | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: Prof. Rajashree Chaudhry | [6 empty] | DATE: 4-3-26 | [11 empty] | 2024-10-08
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Ashokkumar Bhati Ayush Balip | 2026-01-08 | 2026-01-16 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.2 | Identifying the functionalities of the Mini Project | Ashokkumar Bhati Ayush Balip Keval Shah Sameer Saiyed | 2026-01-16 | 2026-01-28 | 2 | 100% | bar: WEEK 2 M to WEEK 3 F
1.3 | Discussing the project topic with the help of paper prototype. | Ashokkumar Bhati Ayush Balip Keval Shah Sameer Saiyed | 2026-01-28 | 2026-02-05 | 1 | 100% | bar: WEEK 4 M to WEEK 5 F
1.4 | Designing the Graphical User Interface (GUI) | Aayush Balip | 2026-02-05 | 2026-02-11 | 1 | 100% | bar: WEEK 5 M to WEEK 7 F
1.5 | Presentation I | Ashokkumar Bhati Ayush Balip Keval Shah Sameer Saiyed | 2026-03-06 | 2026-03-06 | 1 | 100% | bar: WEEK 8 M to WEEK 8 F
2 | Project Design and Implementation
2.1 | Database Design | Ashokkumar Bhati Ayush Balip | 2026-02-17 | 2026-03-03 | 3 | 100% | bar: WEEK 9 M to WEEK 12 F
2.2 | Database Connectivity of all modules | Aayush Balip | 2026-03-03 | 2026-03-13 | 1 | 100%
2.3 | Integration of all modules and Report Writing | Ashokkumar Bhati Ayush Balip Keval Shah Sameer Saiyed | 2026-03-13 | 2026-03-31 | 1 | 100% | bar: WEEK 12 M to WEEK 13 F
2.4 | Presentation II | Ashokkumar Bhati Ayush Balip Keval Shah Sameer Saiyed | 2026-03-31 | 2026-04-01 | 1 | 100% | bar: WEEK 14 M to WEEK 14 F