## Gantt Chart
PROJECT TITLE: |  |  | DataPrepX – AI Enhanced Survey Data Preparation System | [14 empty] | INSTITUTE & DEPARTMENT: A.P. Shah Institute of Technology ¦ CSE (Data Science)
PROJECT GUIDE: |  |  | Ms. Priyanka Karhade | [14 empty] | DATE: Academic Year 2025–26
[7 empty] | PHASE ONE | [5 empty] | PHASE TWO
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | END DATE | DUR. (Wks) | PERCNT. COMPLETE | WEEK 1 Jan W3 | WEEK 2 Jan W4 | WEEK 3 Feb W1 | WEEK 4 Feb W2 | WEEK 5 Feb W3 | WEEK 6 Feb W4 | WEEK 7 Mar W1 | WEEK 8 Mar W2 | WEEK 9 Mar W3 | WEEK 10 Mar W4 | WEEK 11 Apr W1 | WEEK 12 Apr W2
Project Conception and Initiation
1 | Group formation and topic finalization (DataPrepX title, scope, objectives) | Harsh Lad Siddhesh Surve Aryan Shelar Sujal Jain | 7/1/25 | 7/1/25 | 1 | 100%
1.1 | Literature review — imputation, outlier detection, Auto-Prep pipelines (5 papers) | Sujal Jain Aryan Shelar | 14/1/25 | 21/1/25 | 2 | 100%
1.2 | Identifying features and functionalities of DataPrepX (AI Confidence Calibration concept) | Aryan Shelar Sujal Jain | 14/1/25 | 21/1/25 | 2 | 100%
1.3 | Discussing the proposed system architecture and 13-endpoint REST API design | Harsh Lad Siddhesh Surve | 21/1/25 | 28/1/25 | 2 | 100%
1.4 | Designing the graphical user interface (Tailwind CSS glassmorphism wireframes) | Harsh Lad Siddhesh Surve | 28/1/25 | 28/1/25 | 1 | 100%
1.5 | Presentation I | Harsh Lad Siddhesh Surve Aryan Shelar Sujal Jain | 4/2/25 | 4/2/25 | 1 | 100%
Project Design and Implementation
2 | Database / Storage Design (GCS bucket structure, /tmp layout, job metadata schema) | Siddhesh Surve Aryan Shelar | 4/2/25 | 4/2/25 | 1 | 100%
2.1 | Flask REST API backend — auth endpoints, upload, DataProcessor pipeline | Harsh Lad Siddhesh Surve | 4/2/25 | 11/2/25 | 2 | 100%
2.2 | React frontend — Upload, ConfigForm, ReportView components + Tailwind theme | Aryan Shelar Sujal Jain | 4/2/25 | 11/2/25 | 2 | 100%
2.3 | AI Confidence Calibration module (ConfidenceCalibration class, scoring formulas) | Harsh Lad Siddhesh Surve Aryan Shelar Sujal Jain | 11/2/25 | 18/2/25 | 2 | 100%
2.4 | VisualizationGenerator — 6 PNG chart types, DataPrepX dark theme, 300 DPI | Siddhesh Surve Aryan Shelar | 18/2/25 | 25/2/25 | 2 | 100%
2.5 | Integration of all modules — CORS, JWT security, end-to-end testing | Harsh Lad Siddhesh Surve Aryan Shelar Sujal Jain | 25/2/25 | 4/3/25 | 2 | 100%
2.6 | Cloud deployment — Cloud Run backend, Firebase Hosting frontend, GCS IAM | Harsh Lad Sujal Jain | 4/3/25 | 11/3/25 | 2 | 100%
2.7 | Report writing, diagrams, and final documentation | Harsh Lad Siddhesh Surve Aryan Shelar Sujal Jain | 18/3/25 | 25/3/25 | 2 | 100%
2.8 | Presentation II | Harsh Lad Siddhesh Surve Aryan Shelar Sujal Jain | 25/3/25 | 25/3/25 | 1 | 100%
LEGEND — Task Owner Color Coding
All Members (Harsh, Siddhesh, Aryan, Sujal)
Harsh Lad & Siddhesh Surve
Siddhesh Surve & Aryan Shelar
Aryan Shelar & Sujal Jain
Harsh Lad & Sujal Jain